## Slide 1
Gantt Chart
© 2012 Project Lead The Way, Inc.
Introduction to Engineering Design

## Slide 2: History of the Gantt Chart
Henry L Gantt, an American engineer in 1917, developed a horizontal bar chart used as a production control tool. The Gantt chart provides a graphical illustration of activities to be completed according to a specific time schedule. On the left side of the chart is a list of activities. Along the top is the time frame during which each activity is to be completed.

## Slide 3: Sequential and Parallel Tasks
Project planning organizes tasks
Task types:
  Sequential or linear
    Task dependent on completion of another task
  Nondependent or parallel
    Task not dependent on completion of any other tasks
    Tasks may be done at any time before or after a particular stage is reached
Notes: An essential concept behind project planning is that some tasks are dependent on other tasks being completed first. It is not a good idea to start building a house before you have designed it! These dependent tasks need to be completed in sequence, with each stage being completed before the next tasks can begin. We can call dependent tasks sequential or linear. Other tasks are not dependent on completion of any other tasks. These may be done at any time before or after a particular stage is reached. These are nondependent or parallel tasks.

## Slide 4: Gantt Chart: Virtual Design Activity

## Slide 5: Gantt Chart Example
What tasks are needed to build a house?
In what order do the tasks need to be performed?
Can any tasks be performed at the same time as another task?

## Slide 6: Gantt Chart: House Construction
Ground

## Slide 7: Gantt Chart: House Construction
Ground
Foundation
Foundation work starts as site is cleared

## Slide 8: Gantt Chart: House Construction
Ground
Foundation
Floor
Floors can start after
Foundation is completed

## Slide 9: Gantt Chart: House Construction
Ground
Foundation
Floor
Walls
Landscape

## Slide 10: Gantt Chart: House Construction
Ground
Foundation
Floor
Walls
Roof
Roof is partially constructed as walls are being built

## Slide 11: Gantt Chart: House Construction
Ground
Foundation
Floor
Walls
Roof
Siding
Siding started once walls are complete and while roof is being built

## Slide 12: Gantt Chart: House Construction
Ground
Foundation
Floor
Walls
Roof
Siding
Landscape
All tasks are complete